## Slide 1: F&UM Deep-Dive with Ray
20 October 2026
Notes: Purpose: give Ray one view of what the platform team accomplished since September, what is ahead, and the decisions that keep trading GA at the end of May possible.

## Slide 2
Contents
1
Where we are and what is ahead
2
Unified Access Request Management
3
Multi-Firm: parent firms & sub-advisors
4
Self-serve User Management
5
Unified CX User Attestations
6
Decisions and asks

## Slide 3: Where we are — accomplished and ahead
F&UM Deep-Dive with Ray
Accomplished · September–October 2026
✓
Ownership — Knowledge transfer from Penny complete; FUM, access, security and firm hierarchy now under one platform PM
✓
Employee Access — IIQ integration delivered; employee migration running in phases
✓
Secured Zone SSO — Integration and navigation in build for CX 6.0 (end of October)
✓
Unified Access Management — Design complete (6 flows, prototype validated against 20 Okta packages); scope cut; Feature Onboarding Plan ready for engineering
✓
Multi-Firm — Discovery done (4 client sessions, RVP review, data analysis); PRD drafted; Firm360 Parent_Code change in flight
✓
Platform governance — Feature-registration process in place; position on FGDA set; Infinite integration clean-up assessed
Ahead
Q4 2026
CX 6.0 / 8.0
Secured Zone SSO live · UAR build starts (PCR, feature registry, request form) · Multi-Firm delegation requirements and governance with Ed, Jonathan and Ray
Q1 2027
by end Feb
UAR and self-serve user list complete · Multi-Firm design closed with Owen and JP · Firm360 relationship model agreed
Q2 2027
Mar–May
Multi-Firm build in March–April → beta and pilot with non-sub-advisory firms → trading GA at the end of May
H2 2027
after GA
Parent-aware attestations · usage reporting to Firm360 · R2 powered down on October 31 (~$5M a year)
Notes: Talk track: six weeks in, the three foundations are moving — Employee Access delivered, SZ SSO in build, UAM designed and ready for engineering — and Multi-Firm discovery is finished. The right column is the sequence we must hold to reach trading GA in May.

## Slide 4: The line in the sand: trading GA at the end of May 2027
F&UM Deep-Dive with Ray
Trading cannot launch without Multi-Firm: sub-advisors trade across firms and survive today on NetRep and R2. Everything in front of Multi-Firm sets its start date.
Oct 2026
Today · Q1 planning in 2 weeks
End Oct
CX 6.0: SZ SSO + employee SSO
Dec 2026
Orders thin launch · trading beta
Feb 2027
UAR + user list complete (target)
Mar–Apr
Multi-Firm build (one full quarter)
End May
Trading GA · Multi-Firm drop-dead
Oct 31, 2027
R2 powered down
UAR build · Q4 → Q1
Self-serve user list · Q1
Multi-Firm · Mar–Apr
Trading GA · end of May
Parent-aware attestations · H2 2027
Dependency chain
Why Multi-Firm gates trading
Sub-advisors need to trade on accounts of several firms from one profile. Without the relationship model, trading would launch only for single-firm users and the sub-advisory book stays on NetRep.
Why UAM gates Multi-Firm
Parent and delegated access are expressed through the unified request form, the feature registry and the user list. Multi-Firm extends them; it cannot be built first.
What the R2 sunset does not fix
October 31, 2027 removes R2, not the duplicate identities. Every SZ and R2 ID must be linked behind a CX profile before then, which is Multi-Firm plus UAM.
Notes: Talk track: one picture of the dependency. If UAR finishes in February, Multi-Firm gets March and April and trading launches in May. Each week UAM slips moves the whole chain; the R2 power-down date does not help with any of it.

## Slide 5: Executive Summaries
Notes: Four deep-dives follow, each with the same structure and a visual index: stage, value, risk, effort, urgency, and what it enables or depends on.

## Slide 6: Unified Access Request Management
F&UM Deep-Dive with Ray
Executive Summary
Design complete: six user-flow specifications (manage integrations, features, firm users, requests, monitoring, processing) with Figma, plus a clickable prototype validated against 20 production Okta packages Feature Onboarding Plan written for engineering: P0–P3 prioritization and alpha → beta → pre-prod → prod gates; handover to the delivery team is the next step Scope trimmed to what reaches production in Q1: provisioning automation, NetRep and external apps, and case management are deferred (legacy forms stay for those) Enabler for Multi-Firm: the request form, feature registry and catalogue are what parent/child and delegated access will extend
Top Three Discussion / Decision Points | 
Scope & estimation | Engineering estimate pending. Hold v1 to P0 plus the provisioning diff and steward monitoring so build completes by end of Q1 and Multi-Firm can start in March.
Non-standard IDs | About 600 of ~9,000 users (multi-firm RR codes, SZ/NetRep-only IDs) will not fit the new form. Approve the tactical path — legacy forms and tickets via Radhika and ID Admin — until Multi-Firm removes the need.
Client change | Retire R2 myRequest, the iMOST Unified Access Form and the R2 steward portal only after adoption; announce how NetRep and external-app requests continue.
Objective(s) / Purpose(s)
One intake in CX to create, update and deactivate access across CX, Secured Zone and R2 A catalogue (system → capability → feature → module) replacing the registry spreadsheet ID Admin works from structured, per-system instructions within the 48-hour SLA Firm security stewards see request status and their user list in CX
Benefit(s) / Problem(s) to Solve
Three request channels today, free-text RR instructions, 2 days to 2 weeks to provision Three misregistration incidents in 2026, plus a live client given an untested orders module (Nov 2025) Auditable trail from request to access; one-time credential handling Foundation for Multi-Firm, self-serve user management and CX attestations
Solution Approach
System Access Configuration (integration registry), platform inventory and feature-management enhancements feed the form PCR schema: service, capability, access right, instruction, parameter, system, request, requested user, secret Unified request form with firm filtering and required parameters; lifecycle submitting → submitted → under review → complete / rejected / cancelled ID Admin processing workspace with provisioning diff, one-time credential release and steward monitoring Rollout: alpha on NBIN Internal → beta with selected firms → pre-prod → production waves
STAGE
VALUE
RISK
EFFORT
URGENCY
ENABLES → / DEPENDS ON ←
Discovery
Design
Build
Launch
→ Multi-Firm, self-serve user list, CX attestations
← SZ SSO (end Oct), feature registry, engineering capacity
Notes: Talk track: design is done and validated; the ask is to protect the P0 scope and the Q1 completion date because Multi-Firm cannot start until the form and catalogue exist. Three decisions: hold scope, approve the tactical path for ~600 non-standard IDs, and agree the client communication for NetRep/external apps staying on legacy forms.

## Slide 7: Multi-Firm: parent firms & sub-advisors
F&UM Deep-Dive with Ray
Executive Summary
Compass enforces one user = one firm, yet ~40% of firms are multi-firm: 85 parent groups with 184 child firms and 45 sub-advisors serving 35 firms — handled today with extra IDs or RR-code workarounds nobody can prove legitimate Discovery complete (Harbourfront, Guardian, Fiera, RN Croft, RVP review, data analysis); PRD drafted for parent/child; delegation requirements are being written now with Risk Hard dependency: CX trading GA at end of May 2027 needs sub-advisors on Compass, so Multi-Firm must be built in March–April — requirements and design must close in Q4/Q1 Platform-wide change (FNUM, Accounts, Orders, Servicing, SZ, attestation): the concept must be concrete before build, and dependencies delivered together
Top Three Discussion / Decision Points | 
Firm360 as source | Parent/child already lives in Firm360 (new 8-character Parent_Code); delegation does not exist there yet. Decide the feed (API vs nightly file), who builds the delegation table, and the products & services redesign timing.
Sub-advisor identity | One ID with several feature profiles (roughly three extra months of platform work) or two credentials — home firm plus a trading-only sub-advisory profile. Needs an engineering estimate and a call against the May date.
Governance first | Who authorizes, attests and revokes delegated access, and signature-based agreements (Ed, Jonathan). Related: keep NBIN’s own RR store rather than depend on the wealth FGDA shared service.
Objective(s) / Purpose(s)
Model parent/child and delegation in CX, synchronized with Firm360 One ID per person, scoped to every firm they legitimately serve, with firm context always visible Parent-level provisioning, aggregate views and attestation; delegated access limited to what the relationship allows Unblock CX trading; prerequisite for SZ SSO and FGDA for parent users
Benefit(s) / Problem(s) to Solve
A Harbourfront user can carry up to 28 IDs (7 CX, 7 NetRep, 7 SZ); 627 people hold 2–5 Secured Zone IDs Invalid cross-firm access was found only after weeks of analysis; Secured Zone checks no firm boundary Attestations cannot see parent users; leavers keep forgotten IDs Strategic: parent/child grows with M&A (Harbourfront–Cumberland); sub-advisory is the near-term gate for trading
Solution Approach
NOW: parent firm set up from Firm360 as a firm with a global parent package; parent FSS; UAR extended to choose firm context (parent, child, delegated firms); cross-RR access and aggregate views in core apps NOW: delegation registered in the CX firm profile (type → permitted features); home firm administers users, delegating firm confirms and can revoke NEXT: parent-aware attestation, usage reporting to Firm360, relationship termination that cascades access removal Out of scope: parent-of-parent, automated feature inheritance, bulk loads, firm self-serve settings Legacy: SZ and R2 IDs linked behind the CX profile; nothing fixed in R2 (powered down Oct 31, 2027)
STAGE
VALUE
RISK
EFFORT
URGENCY
ENABLES → / DEPENDS ON ←
Discovery
Design
Build
Launch
→ Trading GA (May 2027), SZ parent-user SSO, full attestations
← UAR + user list, Firm360 relationships, governance decisions
Notes: Talk track: this is the strategic and the time-critical item at once. Discovery is done; what remains is three decisions that only Ray can move — Firm360 as the system of record for relationships, the identity model for sub-advisors, and governance ownership with Risk. If any slips, trading slips.

## Slide 8: Self-serve User Management
F&UM Deep-Dive with Ray
Executive Summary
Firms have no view of their own users in CX; the internal list is not client-ready — statuses disagree between FNUM and Okta and resources are unlabelled Right-sized scope for Q1: externalize a correct user list and start the next action (modify, deactivate) from it; password reset, 2FA and full attestation deferred Sequenced right after UAR; needed before Multi-Firm so a parent steward can see users across the group Enabler for Unified CX User Attestations: no list, no attestation
Top Three Discussion / Decision Points | 
Minimum scope | List plus initiate action, or add password reset and 2FA? Recommend the minimum — every addition pushes Multi-Firm.
Data fix first | FNUM/Okta status discrepancies (Candi’s FUM-187/258, open since 2023) must be corrected before clients see the list.
Packaging | Create the externalizable steward package (user list + unified request) separate from internal platform-admin resources.
Objective(s) / Purpose(s)
Stewards see all their users, status and packages, and act from the list One view per person, including linked SZ and R2 IDs Foundation for attestation and parent-group oversight
Benefit(s) / Problem(s) to Solve
Guardian, Harbourfront and Fiera asked for a consolidated view of who has access Removes a class of ID Admin tickets and shortens offboarding gaps Clears a list of defects accumulated since the 2023 launch
Solution Approach
Reuse the UAR data model: user list under Manage Firm Users with filters, profile modal and export Statuses sourced from Okta (source of truth); platform-admin resources hidden from firms Deactivate = one request disabling all linked IDs; Multi-Firm later extends the list to parent context
STAGE
VALUE
RISK
EFFORT
URGENCY
ENABLES → / DEPENDS ON ←
Discovery
Design
Build
Launch
→ CX attestations, parent-group oversight
← UAR, FNUM/Okta data cleanup
Notes: Talk track: small if kept small. The decision is to keep it to the list and the next action, fix the status data first, and package it so firms never see internal admin resources.

## Slide 9: Unified CX User Attestations
F&UM Deep-Dive with Ray
Executive Summary
Attestation today is files: quarterly CX reports per firm over SFTP, annual R2/SZ/NetRep reports, reconciled by hand with no relationship tags; Harbourfront could not reach the SFTP drop, Guardian cannot tell which report arrived Target: attestation inside CX from the user list — review, confirm and revoke in one place, with an evidence trail Achievable without Multi-Firm, but it would miss parent users and delegated access — exactly the gaps auditors ask about; plan a first wave after the user list, the full version after Multi-Firm
Top Three Discussion / Decision Points | 
Sequence | v1 per firm in CX after the user list (Q1/Q2) or wait for Multi-Firm? Recommend v1 then extend — partial value early, no rework if built on the same list.
What is certified | Today: should this user still exist. Tomorrow also: does the delegating firm confirm the sub-advisory relationship still stands?
Retiring the files | Stop SFTP attestation only once CX attestation covers linked SZ and R2 IDs.
Objective(s) / Purpose(s)
Self-serve attestation in CX with an auditable record Parent users and delegated access visible and attributable Less manual reconciliation; fewer missed deactivations
Benefit(s) / Problem(s) to Solve
Addresses audit and OSFI findings on access governance Leavers found only at quarterly review (RN Croft); lingering access across two cycles (Fiera); stale access confirmed by RVPs Secured Zone grants more than R2 and NetRep for the same person — visible once reconciled
Solution Approach
Build on the user list: attestation campaign per firm; attest or revoke actions feed UAR deactivation Reconcile linked NetRep and SZ IDs (NetRep user-id parameter; P2 in the onboarding plan) Multi-Firm adds parent-level campaigns, relationship tags and delegating-firm confirmation
STAGE
VALUE
RISK
EFFORT
URGENCY
ENABLES → / DEPENDS ON ←
Discovery
Design
Build
Launch
STAGE backlog · after user list
→ Audit compliance, safe R2 exit
← User list; Multi-Firm for full value
Notes: Talk track: a lower-urgency, high-value item. It can start before Multi-Firm on the user list, but the parent and delegation views only arrive with Multi-Firm, so position it as two waves.

## Slide 10: Decisions and asks
F&UM Deep-Dive with Ray
Six items that need your sponsorship or a decision in the next weeks — ordered by what they unblock.
# | Decision / ask | Why it matters now | Owner | By
1 | Hold UAM v1 to P0 (+ provisioning diff, steward monitoring); confirm the deferrals: provisioning automation, NetRep and external apps, case management | Protects the Q1 finish and the Multi-Firm start | Ray · Kevin | Q1 planning (2 weeks)
2 | Firm360 as the system of record for firm relationships: Parent_Code feed (API or nightly file), a delegation table, products & services redesign timing | CX design assumes it; sub-advisory does not exist in Firm360 today | Ray | November
3 | Sub-advisor identity model: fund an estimate for one ID with several profiles vs two credentials, then decide against the May date | Decides the size of the Multi-Firm build | Esther · JP | November
4 | Governance pack for delegation: who authorizes, attests, revokes; signature-based agreement before any account release | Blocks delegation design and the sub-advisor PRD | Ed · Jonathan | December
5 | FGDA: NBIN keeps its own RR store; adopt wealth’s shared service only behind an edge architecture, and last | Avoids a critical-path dependency on an untested shared service | Ray · Kevin with JP | Before the wealth design review
6 | Capacity: Tech Titans for the FNUM notification endpoints; PO hire; cover for Candi from October 22 | FNUM team is fully stacked through Q1 | Kevin | Now
Notes: Talk track: close by asking for the six things. Items 1–3 set the critical path; 4 and 5 remove design risk; 6 is capacity. Propose a 30-minute follow-up with Kevin to confirm owners and dates.